## Trial Hole 6
Trial Hole Report Sheet |  |  |  |  | #VALUE!
REFERENCE NUMBER
2402179
SHIFT DETAILS
DATE | 26-02-2025 |  | CONTRACTOR |  | Elmy Solutions Ltd
DAY | Tuesday |  | PROJECT ID (RN) |  | 001 - VH Wokingham
SHIFT | Day |  | CLIENT |  | Volkerhighways
LOCATION | Broad Street |  | PROJECT NAME |  | Broad Street
Trial Hole Location | Outside no 16 |  | PROJECT MANAGER |  | Mihai Prejma
Area | Behind Kerb Line in Footway |  | BOROUGH |  | Wokingham
Work Performance
| Time | Actual | Reason for Delays
Shift Start | 08.00
Finish works: | 16.00
Trial hole Details
|  | Utility | Size | Material | Depth | Cover | Key
|  | water | N/A | N/A | N/A | N/A | W
|  | Gas | N/A | N/A | N/A | N/A | G
|  | Electric | N/A | N/A | N/A | N/A | E
|  | Telecom | N/A | N/A | N/A | N/A | T
|  | Catv | N/A | N/A | N/A | N/A | C
|  | Drainage | N/A | N/A | N/A | N/A | F/SW
|  | Other: Tree Roots | 50-120mm | Wood | 200-300mm | 200-300mm | Tree Roots
Obsevations
Tree roots present at 200-300mm in depth. Please see pictures for reference.
Method of Excavation | Trial Pit Depth below Ground Level | Trial Hole Dimensions
Jack Hammer & Hand Dig | 0.6m | 1000x1000mm
Reinstatment Issues
NO. Reinstated using same make up as the existing footway
Report Completed By ELMY
Name | Daniel Rotaru
Date | 2025-02-26
Signature | REDACTED
Agreed By
Name | Mihai Prejma
Date | 2025-02-26
Signature | REDACTED
Ground Makeup and dimensions
0m - 0.1m in depth
63mm ASP Slabs & 30mm Sand Bedding
0.1m - 0.3m in depth 200mm Concrete Base
0.3m to 0.6m in depth 300mm Stiff Ground