## Sheet1
1894-KC-XX-YTREE-TreeSchedule-RevC |  |  | Date of survey: 08/04/2026
Schedule of trees on land at Watmore Lane, Winnersh, Berkshire
TPO Ref 1773/2021 | Tree No. | Species | Action
TPO Ref
W2 | 11 | Outgrown hedgerow of predominantly hawthorn | Clear 1 metre wide corridor north west of tree 20 to enable installation of reptile barrier.
W1 | 27 | Group of predominantly blackthorn | Cut back blackthorn encroachment on south eastern side of group to enable installation of reptile barrier (this is mostly related to scrub that lies outside the boundary of W1 but some stems within W1 may be impacted).
A2 | 30 | Hedgerow of predominantly ash and hawthorn | Prune to provide circa 1 metre wide tunnel through group to enable installation of reptile barrier.
A2 | 34A | Group of ash saplings | Prune to provide circa 1 metre wide tunnel through group to enable installation of reptile barrier.
A2 | 48 | Group of predominantly blackthorn with occasional hawthorn | Prune to provide circa 1 metre wide tunnel through group to enable installation of reptile barrier.
A2 | 52 | English oak | Remove dead branches to enable installation of reptile barrier.
A2 | 57 | Ash | Remove basal shoots to provide clearance to install reptile barrier.
A1 | 61 | Ash | Remove basal shoots to provide clearance to install reptile barrier.
A1 | 63 | Group of elm saplings and field maple | Prune to provide clearance to install reptile barrier.
A1 | 64 | Hawthorn | Prune to provide clearance to install reptile barrier.
A1 | 76 | Cluster of hawthorn and goat willow | Prune to provide circa 1 metre wide corridor to enable installation of reptile barrier.
A1 | 80A | Group of mixed broadleaves | Prune to provide circa 1 metre wide corridor to enable installation of reptile barrier.
A3 | 82 | Hedgerow of predominantly hawthorn and elm | Prune to provide circa 1 metre wide corridor to enable installation of reptile barrier.