## Sheet1
Emy Comments 09/04/2025 on Phasing Document (rev D) |  | Updates Made 21/05 (Rev E)
CIL | The phasing condition is primarily for planning purposes but also has bearing on CIL payments and, as you are aware from our conversation on Friday, the CIL Team have concerns about how the proposals fit with CIL legislation. My understanding is that, because of the background, each reserved matters will need to be treated as a separate chargeable development, rather than being split into smaller phases. However, they potentially have more flexibility with the approach to instalments, which they will be willing to discuss. As it is a separate procedural matter, they will liaise with you separately about the CIL aspect of the phasing. | No changes to the document - sub phasing has remained
| Related to this, from discussion between Nick and Jean at the Tuesday meetings it appears that there is still an aspiration to redistribute soil between parcels. If so, as discussed previously, this will need to be identified as a separate phase of works in order to avoid the removal or deposit of material being considered as commencement of each parcel for CIL purposes. | Shown on the breakdown table on page 8 - 11
General Comments | The table on page 05 would be useful but several of the page references need updating.
| Although it is not directly a planning matter the document should acknowledge and confirm that the Homes England funding profile will be met. | New text included at 1.11
| There are a number of elements of the development that have not been covered and need to be (including on the plan/summary tables): | Extended breakdown table shown on page 8 - 11
| SANG, the school and neighbourhood centre. SANG and the neighbourhood centre are discussed further below. For the school I suggest showing the earliest and latest delivery dates on the summary phasing table and including a paragraph in the text. | Shown on breakdown table on page 8 - 11 Additional text from Matt on page 95
| Where the opening of the SWDR and Heathlands link are expected to fit in the timeline (accepting that this is not in the consortium’s control). How many occupations could there be before these routes are open and how will any dwellings occupied before then gain access? This will need to be covered in the summary and also under criterion vi) | shown on breakdown table on page 8 - 11 and additional text at 3.3
| The early delivery of the R10/R14 link (albeit under a separate planning permission) should be identified as a phase because of the implications for criterion vi) | Shown on the breakdown table on page 8 - 11
These items should be included in the summary tables as well as the detailed sections of the document.
| Rather than “Master Phase”, I suggest using “Development Zone” for consistency with the S106. (This may also assist with future discussions with the CIL team). | Changed throughout the document
| There in an inconsistency between the lefthand table on page 07, which indicates phase R10.2 is to be delivered in year 2 and the righthand table that shows it in year 1. | Updated to be consistent
| Triggers for POS generally fall within the same year as adjoining residential phases, so it seems an unnecessary complication to separate them into separate phases. Should the phasing be accepted as a structure for CIL payments (which admittedly seems unlikely at the moment), this would also result in significant and avoidable administrative burden. If the landscaping is kept as separate phases, it would be helpful to include them in the summary phasing table. | no changes to the phasing - GI areas included on breakdown table on page 8 - 11
| Miller don’t seem to be delivering any housing in year 5. Is this correct? | Table shows Miller working on R13 in year 5
the number, size, type and tenure mix of affordable dwellings, demonstrating overall delivery of 35% affordable homes, appropriately distributed across the development | The proposed size, type and tenure mix is consistent with the S106 obligations and suitably phased across the development, except for the split between social and affordable rented, which is needed to demonstrate that the minimum of 58% social rented and 4-12% affordable rented will be achieved and appropriately distributed across the site. | Additional text 3.15
| Once agreed, the Framework Affordable Housing Scheme will address the S106 obligation too. | No change to the document
the number and size of housing to be built to M4(2) standard (accessible and adaptable dwellings) or equivalent which should amount to at least 5% of the affordable housing, consisting of one and two-bedroom flats in clusters of 8 – 10 units and at least 5% of the market housing; | Although pages 08-09 make reference to the number and size of M4(2) standard dwellings this information has not actually been included. The distribution across the phases needs to be understood or, if the intention is that each phase should consume its own smoke, then that should be specified, together with the number of affordable and market dwellings. | Numbers included in the table on page 13
There may be some further comments to come on how this provision might meet current specialist housing needs.
the size and type of market dwellings in general accordance with the Wokingham Borough Local Housing Needs Assessment 2019 Report of Findings (January 2020) or any policy and guidance that supersedes it; | The proposed market housing mix is provided on pages 06-09 but there is no consideration of how it relates to the Local Housing Needs Assessment (LHNA) 2023. The key figures are summarised in the supporting text under Policy H1 of the Proposed submission Plan (repeated below). The proposed mix would provide a greater proportion of one, two and three-bedroom properties and a correspondingly small proportion of larger properties, the reason for which needs to be satisfactorily explained. | Separate note
| In addition, there is a S106 requirement for at least 20% of dwellings occupied by 31 March 2026 to be flats and at least 14% of the completed development and it needs to be demonstrated that the delivery profile will achieve this. | Additional text 3.10 and 3.16
on-site public open space; | The proposed triggers for delivery are generally consistent with the S106 obligations. However, there are a few omissions that need to be addressed.
| While the trigger for the SANG deliver strategy is prior to commencement, the phasing cannot be complete without an indication of how this dovetails with housing delivery, ensuring that SANG is available before first occupation of any dwelling within the development. I understand that the Strategy is close to being agreed and the intention, which would be the best approach as it would allow the two to be considered in parallel. | SANG shown on breakdown table on page 8 - 11
| The timing of delivery of P1, ASO5, ASO6 & AOS6a also need to be included. Delivery of P1 depends on the phasing of the Holme Park SANG (if any). AOS6 & AOS6a fall within R11.4, so it would seem sensible for them to be delivered alongside it. AOS5 falls between the four phases of R11. Given deliver of AOS6 & AOS6a is to be relatively late, an earlier trigger, alongside R11.1 or R11.2 would make sense. | P1 - coming forward y3 alongside northern area of HPS AOS5 Y2 AOS6/6a Y4
| Referring to the the comments in relation to criterion xi), the timing of delivery of PAG3, NGS9iv and NGS6ii needs to be revised for consistency. | PAG3, NGS9iv commence in Y1 NGS6ii commence in Y2
the neighbourhood centre incorporating civic space; | the proposed timing of delivery is acceptable but this should be included in the summary phasing table. | Neighbourhood centre added to summary table on page 8-11
phasing of delivery of the movement network to facilitate sustainable access for residents to key on and off-site destinations, including SANG, play areas, schools and bus stops within the SDL; | This criterion needs quite a bit more work, especially in relation to the early phases. It is about how residents are going to access facilities during the construction phase rather than once development is complete, so requires more thought about what facilities will/won’t be in place as each phase comes forward. It is not sufficient to rely on the major routes being open (and will they even be open on first occupation of the early phases?). The R10/R14 link road has a 9 month construction period, so probably will be but the SWDR and Heathlands link have a two year construction period, so there could be occupations before they are open. | New movement network plans shown page 18 - 27
| Explanatory notes alongside the drawings would assist. | Notes added to plans
| This goes back to the point about the summary phasing table needing to show all infrastructure, not just housing delivery. It needs to be set out where the destinations are eg Floreat Montague Park school for early phases, the new school south of the railway later. We also need to understand the SANG strategy too. At Anne’s SANG has limited spare capacity (fewer than 200 dwellings) so Holme Park is likely to be needed by year two, if not sooner. Travel habits establish quickly so people need to have an attractive walking route from the start. For R10 & R11.1 and R11.2 to Holme Park, early residents should be able to use WWFP5, which ought to be open or an alternative route throughout construction. This suggests early deliver of PAG3 (R11.2/year2), NGS8 (R11.3/year3), AOS4 (R11.3/year3) , NGS6i (R11.3/year 3) and works on Easthampstead Road (H2, completion prior to occupation of first dwelling that relies on Holme Park SANG) | Shown on new movement plans New text 4.1- 4.4
| For R11 you will be building from east to west. At what point will the connections through to the Heathlands Link be formed and useable? Need to consider period when emergency access will be needed and when it can be closed? | New movement plans and included on summary tables page 8 - 11
| R13. How will ① provide sustainable access to the SANG if R7 doesn’t exist? Also, will the school and local centre be there are that point or will they still be relying on Floreat Montague Park? If R7 isn’t commencing until year 6, and R13 is 117 dwellings how will emergency access be achieved or will the route through to Easthampstead Road be constructed early, in which case the phasing should be explicit about that. | Temp emergency access shown on plans in y5 and y6 until R7 comes forward
| Access from R4 to Holme Park SANG will be difficult until R5 and neighbourhood centre come forward. Is there any opportunity to change the order of delivery in R4 and R5 or for early deliver of routes through R5 to the SANG? | y7 NGS2 and Footpath 10 commence to provide off road access
parking for SANG visitors prior to the permanent provision in the neighbourhood centre becoming operational; | This is confusingly dealt with on page 74 under the car club heading and it would be better to separate the two issues. The proposals in paragraph 6.3 are acceptable but it would be clearer if the first sentence specified interim car parking. | Heading added on page 82
timing and delivery of the flood compensation works associated with the SWDR; | The Strategic Infrastructure drawing shows Thames Water culvert and Holme Park Basin as No 1. Subject to confirmation that the numbering reflects the sequence of events the details relating to deliver of flood compensation works are acceptable. The Environment Agency have made this point and highlighted that the floodplain compensation should be operational before development of phases R7, R8, the school or the neighbourhood centre. | Shown on breakdown table on page 8 - 11
timing of the delivery of the drainage and SuDS in relation to the development it is to serve; | This is covered satisfactorily. | No action required
public art pursuant to condition 8; | The proposals on page 75 are consisted with the Public Art Strategy (P19-0052_44C) but there are a couple of points that need clarification.
| What is the timing for completion of landscaping within the Holme Park SANG following of the hard and soft landscaping? If SANG delivery is phased, it may not be appropriate to wait until the whole SANG is complete. | Shown on breakdown table on page 8 - 11 Design workshops etc starting in the same year as open space works commence with installation the following year
| Paragraph 6.7 indicates the pieces within the Central Parkland will be “set out following the completion of the hard and soft landscaping within all areas”. This requires clarification. Delivery of the art in each park, once the landscaping of it is complete would be acceptable; delaying delivery until the final park is complete in year six would not be. | Clarified to be in line with approved public art document. 1no piece within parks and garden. Have suggested it's included south of R8 in PAG2
early delivery of landscaping required to mitigate the impact upon the listed buildings Britton’s Farmhouse (Grade II) and Barn (Grade II), Lock's House (Grade II*) and Lock's Barn (Grade II) and Wood’s Farm (Grade II); | Brittons Farm: paragraph 6.8 indicates the landscaping within PAG3, within the area shaded in purple (broadly PAG3 excluding P5) will take place first planting season following commencement of R11, which is due to be in year 1. This is acceptable but not consistent with delivery of PAG3 as part of phase 11.0.2 in year 2. The POS phasing should be updated for consistency. | Updated to be consistent
| Locks House & Barn: paragraph 6.9 indicates delivery of NGS11a and NGS9iv during the first planting season following commencement in R10 or R11, both expected to be in year 1. NGS11a already due in year 1 as part of 10.0.1 but NGS9iv is within R11.0.2 (year 2), so will need to be brought forward to year 1 | Updated to be commenced in y1
| Woods Farm: paragraph 6.10 suggests NGS6ii coming forward in year 4 commencement of R13 in year 4. This criterion was intended to secure early delivery of landscaping, where possible, so it could be establishing before the most impactful development commenced. With Brittons Farm and Locks House and Barn, the opportunities are limited because the adjacent development is due to take place early in the programme. In this case, development will not be taking place until year 4, so landscaping should be brought forward in the programme to allow it to be establishing. | Updated to commence in y2
undergrounding of the overhead electricity apparatus; | The key to the Infrastructure Phasing Strategy drawing shows commencement of undergrounding by SSE as No 3 but it is not specified whether the order of the key reflects the order of delivery. It appears to and this should be specified. Completion is shown to be during phase R10.3 i.e. within year 3. These works should be added to the summary phasing table and also there should be a paragraph within the document covering it. | Shown on breakdown table on page 8 - 11
on and off-site highway works necessary to mitigate the impact of the development pursuant to 50, 51 & 52; | The timing of delivery of the three site accesses (condition 50) does not appear to be covered. While the delivery of the SWDR is not in the consortium’s control, the timescale for delivery is known and how it relates to housing delivery needs to be addressed, as mentioned above under general comments. | Shown on breakdown table on page 8 - 11
| Delivery of off-site junctions (condition 51) is consistent with S106 which is acceptable but it is not explicit where the delivery of the R10/R14 link (identified as Ref 2 on the Strategic Infrastructure Drawing) fits in the sequence of events. As it is being delivered early/under a separate planning permission it probably needs to be identified as a separate, early phase. | Shown on breakdown table on page 8 - 11
| The pedestrian and cycle improvements on Easthampstead Road (H2/condition 52 b) seem likely to be triggered by the opening of the Holme Park SANG early in the programme (probably year 1) and this should be set out. Other than that the phasing document is consistent with the S106. | Shown on breakdown table on page 8 - 11
a car club pursuant to condition 49; | This is covered in paragraph 6.2 on page 74 and while what is proposed seems to be satisfactory, the reference to SANG parking is confusing. The neighbourhood centre parking is intended for all visitors to the neighbourhood centre, not just to the SANG and – if paragraph 6.2 is simply saying that the car club will come forward at the same time the neighbourhood centre car parking becomes operational - that will be acceptable. | Heading added on page 82 added for clarification
implementation of the public transport strategy pursuant to condition 48 including details of the bus route. | This is covered satisfactorily. | No action required